## Project Overview
Project Name | Smart Parking Analysis & Prediction System
Project Statement | Manual monitoring of parking lots is inefficient and causes traffic congestion. Drivers waste time looking for empty spots.
Project Description | This system uses computer vision to detect empty parking spots in real-time. It also applies data mining techniques to predict future occupancy rates and analyze revenue based on statistical data.

## Team Members & Roles
Eylül Özdemir | Project Manager, Backend Developer, QA & Tester
Kemal Özkan | CV Engineer, Data Analyst, Frontend Developer

## Budget & Resources
Resource Type | Item Name | Purpose in Project | Cost / License Type
Hardware | 2x Developer Laptops | Code development and model training | Existing (0$)
Hardware | 1x IP Camera / CCTV | Capturing real-time parking lot frames | 150$
Software | Python (OpenCV, Pandas) | Image processing and data analysis | Open Source (0$)
Software | Jira & GitHub | Task management and version control | Student / Free (0$)
Software | Google Teams / Slack | Team communication (Requirement #1) | Free Tier (0$)
Server | Cloud Hosting (AWS/GCP) | Hosting the backend and database | 50$ (Estimated)
Budget Item | Calculation / Description | Estimated Cost (USD)
Human Resources (Labor) | 336 Total Hours x 25$ / hour (Junior Developer Rate) | 8,400$
Hardware & Equipment | IP Camera + Cloud Server expenses | 200$
Contingency Fund | 10% of the total budget for unexpected risks | 860$
TOTAL PROJECT BUDGET |  | 9,460$

## Timeline
Week | Assignment Topic | Smart Parking Project Activity | Deliverable
Week 1 | Introduction & Overview | Defining the "Smart Parking Occupancy & Revenue Prediction" concept and team formation. | Team roster + 1-page project summary
Week 2 | SDLC | Planning the lifecycle: defining camera integration, OpenCV image processing, and data mining phases. | 1-page SDLC diagram
Week 3 | Scope & Requirements | Defining requirements | Requirements document
Week 4 | Work Breakdown Structure | Breaking down the project into Image Processing, Statistical Analysis, and UI modules. | WBS diagram
Week 5 | Gantt Charts | Scheduling tasks like dataset collection, applying resize/blur operations, and model training. | Gantt chart
Week 6 | Resource & Team | Assigning tasks to team members. | RACI matrix
Week 7 | Midterm / Progress | Submitting the halfway point report | Progress report + Updated Gantt
Week 8 | Risk Management | Identifying risks like low camera resolution, weather conditions, or inaccurate data clustering. | Risk register
Week 9 | Quality Assurance | Defining accuracy metrics for the vehicle detection model and testing prediction algorithms. | Test plan
Week 10 | Cost & Budgeting | Estimating costs for IP cameras, local servers, and developer hours. | Budget sheet
Week 11 | Agile Methodologies | Creating sprints for dashboard development and statistical reporting features. | Backlog + Sprint plan
Week 12 | Monitoring & Control | Tracking model accuracy KPIs and system uptime. | Status report with KPIs
Week 13 | Project Presentation | Finalizing the real-time parking spot detection demo and slides. | Slides + Team presentation
Week 14 | Final Review | Compiling all documentation, source codes, and evaluating the project's success. | Final report + Reflection